## 🗺 Overview
⚡ AI APPLICATION DEVELOPMENT — 90-DAY SME ROADMAP
Mon–Fri: 1–1.5 hrs after work ¦ Saturday: 3–4 hrs project build ¦ Sunday: 1.5 hrs review & weekly summary
Phase | Name | Weeks | Days | Focus Areas | Key Deliverable | Total Time/Wk
Phase 1 | Core Foundations | 1–3 | 21 days | LLM APIs · Prompting · Embeddings · RAG · Structured Output | Document Q&A RAG app + streaming chatbot | ~10 hrs/wk
Phase 2 | Production Patterns | 4–7 | 28 days | Agents · Tool Use · Evals · Memory · LangChain · Multi-Agent | Multi-agent research system + eval harness | ~12 hrs/wk
Phase 3 | Production Engineering | 8–10 | 21 days | Latency · Cost · Observability · Security · Deployment | Production-grade monitored REST API | ~12 hrs/wk
Phase 4 | Specialisation & Portfolio | 11–13 | 21 days | Vertical deep-dive · System design · Interview prep · Portfolio | Capstone project + blog post + job applications | ~12 hrs/wk
📅 WEEKLY SCHEDULE AT A GLANCE
Day | Time Commitment | Activity | Notes
Mon – Fri | 1 – 1.5 hrs / day | Focused learning after work | One topic per day, always ship a small deliverable
Saturday | 3 – 4 hrs | Project Build Day | Deep coding session integrating the week's concepts
Sunday | 1.5 hrs | Review & Weekly Summary | Consolidate notes, fill gaps, plan next week
Total / week | ~10–12 hrs | Structured & sustainable | Quality over quantity — rest is part of the plan

## 📘 Phase 1 — Foundations
Phase 1: Core Foundations ¦ 90-Day AI SME Plan
MON–FRI: 1–1.5 hrs learning ¦ SAT: 3–4 hrs build ¦ SUN: 1.5 hrs review & summary
Date | Week | Phase | Day | Topic | What To Study / Build | Deliverable | Time | ✅ Done
▸ WEEK 1 (10 Mar – 16 Mar 2025)
10 Mar | Wk 1 | Ph 1 | 1 | SDK Setup & First API Call | Install Anthropic/OpenAI SDK · send your first /messages call · understand request/response JSON structure · explore role fields | Script: prompt → print response | 1 hr | ✅
11 Mar | Wk 1 | Ph 1 | 2 | Tokens & Context Windows | Understand tokenisation · install tiktoken · count tokens programmatically · learn why context window size matters for architecture | Token counter utility function | 1 hr | ✅ | Done on 12 Mar tokens-context-study
12 Mar | Wk 1 | Ph 1 | 3 | Prompt Engineering I — Basics | Zero-shot · few-shot examples · system vs user messages · role prompting patterns | 5 prompt variations, compare outputs | 1 hr | ✅
13 Mar | Wk 1 | Ph 1 | 4 | Prompt Engineering II — Advanced | Chain-of-thought · XML structuring · negative examples · prompt template class | Reusable PromptTemplate class in Python | 1.5 hrs | ✅
14 Mar | Wk 1 | Ph 1 | 5 | Prompt Engineering III — Practice | Self-consistency · step-back prompting · meta-prompting · test on reasoning tasks | 3 advanced patterns tested + documented | 1 hr | ✅
15 Mar | Wk 1 | Ph 1 | 6 | Week 1 Build Day — CLI Chatbot | Build a multi-turn CLI chatbot with raw API (no frameworks) · conversation history management · streaming responses · error handling | Working multi-turn streaming chatbot | 3–4 hrs | ✅
16 Mar | Wk 1 | Ph 1 | — | Week 1 Review & Summary | Review all 5 topics · write a personal cheat sheet · note gaps · update GitHub README · plan Week 2 | Cheat sheet doc + GitHub push | 1.5 hrs | ✅
▸ WEEK 2 (17 Mar – 23 Mar 2025)
17 Mar | Wk 2 | Ph 1 | 7 | Embeddings Theory | What embeddings are · vector space · cosine similarity · how embedding models differ · use cases overview | Embed 10 sentences, compute similarity matrix | 1 hr | ✅
18 Mar | Wk 2 | Ph 1 | 8 | Vector Databases | Chroma DB setup · CRUD operations · indexing · similarity search · metadata filtering basics | Store & query 100 embeddings in Chroma | 1 hr | ✅
19 Mar | Wk 2 | Ph 1 | 9 | RAG Architecture Deep Dive | Chunking strategies (fixed, semantic, sliding) · overlap · retrieval pipeline design · augmented prompting | Diagram of full RAG pipeline with chunking decisions | 1 hr | ✅
20 Mar | Wk 2 | Ph 1 | 10 | Build RAG — Ingestion Pipeline | Load a PDF · chunk text · generate embeddings · store in Chroma with metadata | Ingestion script: PDF → vector DB | 1.5 hrs | ✅
21 Mar | Wk 2 | Ph 1 | 11 | Build RAG — Query Pipeline | User query → embed → retrieve top-k chunks → augment prompt → stream LLM answer | End-to-end RAG query working | 1 hr | ✅
22 Mar | Wk 2 | Ph 1 | 12 | Week 2 Build Day — Full RAG App | Polish ingestion + query pipeline · add CLI interface · test with 3 different documents · improve chunk quality · handle edge cases (no results, long docs) | Polished document Q&A app | 3–4 hrs | ✅
23 Mar | Wk 2 | Ph 1 | — | Week 2 Review & Summary | Review embeddings + RAG concepts · write a 'How RAG Works' summary in your own words · identify 2 improvements for your app · plan Week 3 | Written RAG explainer + improvement list | 1.5 hrs | ✅
▸ WEEK 3 (24 Mar – 30 Mar 2025)
24 Mar | Wk 3 | Ph 1 | 13 | Structured Outputs | JSON mode · response_format parameter · Pydantic models for validation · instructor library intro | Function that always returns typed JSON from LLM | 1 hr | ✅
25 Mar | Wk 3 | Ph 1 | 14 | Streaming & Temperature | Server-sent events · streaming API implementation · temperature / top_p / seeds · when to use each setting | Add streaming to RAG app · test temp 0 vs 1 | 1 hr | ✅
26 Mar | Wk 3 | Ph 1 | 15 | Error Handling & Retries | Rate limit errors · malformed outputs · retry with exponential backoff · fallback strategies | Robust wrapper with auto-retry | 1 hr | ✅
27 Mar | Wk 3 | Ph 1 | 16 | Polish RAG App | Add structured output · streaming · retry logic · basic logging to your RAG app | RAG app v1.0 production-ready | 1.5 hrs | ✅
28 Mar | Wk 3 | Ph 1 | 17 | Phase 1 Concepts Review | Revisit: APIs · tokens · prompting · embeddings · RAG · structured output — fill any gaps | Personal gap analysis doc | 1 hr | ✅
29 Mar | Wk 3 | Ph 1 | 18 | Week 3 Build Day — Phase 1 Capstone | Build a clean, well-documented RAG app from scratch combining everything: chunking + embeddings + retrieval + structured output + streaming + retries · write a proper README | Phase 1 capstone app on GitHub | 4 hrs | ✅
30 Mar | Wk 3 | Ph 1 | — | Phase 1 Review & Retrospective | Write a Phase 1 retrospective: what you learned, what surprised you, what you'd do differently · update portfolio · plan Phase 2 | Phase 1 retrospective doc published | 1.5 hrs | ✅

## ⚙️ Phase 2 — Patterns
Phase 2: Production Patterns ¦ 90-Day AI SME Plan
MON–FRI: 1–1.5 hrs learning ¦ SAT: 3–4 hrs build ¦ SUN: 1.5 hrs review & summary
Date | Week | Phase | Day | Topic | What To Study / Build | Deliverable | Time | ✅ Done
▸ WEEK 4 (31 Mar – 06 Apr 2025)
31 Mar | Wk 4 | Ph 2 | 16 | Tool / Function Calling Basics | Tool schema definition · how the model decides to call tools · parsing tool_use responses · tool result format | LLM that can call a weather API | 1 hr | ✅
01 Apr | Wk 4 | Ph 2 | 17 | Multi-Tool Agents | Multiple tool definitions · tool chaining · handling tool errors · stopping conditions | Agent with 3 tools: search + calc + file reader | 1.5 hrs | ☐
02 Apr | Wk 4 | Ph 2 | 18 | ReAct Pattern | Reason → Act → Observe loop · implementing the loop · max iterations guard · when to stop | ReAct agent solving 3 multi-step problems | 1 hr | ☐
03 Apr | Wk 4 | Ph 2 | 19 | LangChain Core Abstractions | Chains · runnables · LCEL · prompts · output parsers · when LangChain helps vs hurts | Rebuild chatbot in LangChain LCEL | 1 hr | ☐
04 Apr | Wk 4 | Ph 2 | 20 | LangGraph Intro | Nodes · edges · state · conditional routing · compile + invoke · graph visualisation | Simple 2-node graph routing by intent | 1 hr | ☐
05 Apr | Wk 4 | Ph 2 | 21 | Week 4 Build Day — Agent v1 | Build a multi-tool LangGraph agent: web search + calculator + file I/O + weather · add proper state management · test with 10 real tasks | Multi-tool agent with LangGraph | 3–4 hrs | ☐
06 Apr | Wk 4 | Ph 2 | — | Week 4 Review & Summary | Review tool calling + agent patterns + LangChain · write summary of ReAct vs basic agent · plan Week 5 | Agent pattern comparison notes | 1.5 hrs | ☐
▸ WEEK 5 (07 Apr – 13 Apr 2025)
07 Apr | Wk 5 | Ph 2 | 22 | Evals I — Why Evals Matter | The eval mindset · types: unit, integration, LLM-as-judge · human eval baselines · what to measure | Design eval criteria doc for your RAG app | 1 hr | ☐
08 Apr | Wk 5 | Ph 2 | 23 | Evals II — Build an Eval Harness | Test set creation · automated LLM-as-judge scoring · regression detection · reporting | 10-question eval suite with auto scoring | 1.5 hrs | ☐
09 Apr | Wk 5 | Ph 2 | 24 | Memory Patterns | In-context memory · summarisation memory · entity memory · external stores (Redis) · tradeoffs | Add summarisation memory to your chatbot | 1 hr | ☐
10 Apr | Wk 5 | Ph 2 | 25 | Retrieval Improvements | Hybrid search (BM25 + vector) · reranking with cross-encoders · HyDE · MMR · metadata filtering | Improve RAG with hybrid search + reranking | 1.5 hrs | ☐
11 Apr | Wk 5 | Ph 2 | 26 | LlamaIndex Deep Dive | Index types · query engines · routers · compare to LangChain for RAG use cases | Rebuild RAG in LlamaIndex, compare results | 1 hr | ☐
12 Apr | Wk 5 | Ph 2 | 27 | Week 5 Build Day — Research Assistant | Build: user enters a topic → agent searches web → retrieves 3 docs → synthesises answer with citations · eval suite passes 80% | Research assistant app + eval suite | 3–4 hrs | ☐
13 Apr | Wk 5 | Ph 2 | — | Week 5 Review & Summary | Review evals + memory + retrieval improvements · write 'My Eval Philosophy' doc · update GitHub | Eval philosophy doc + GitHub update | 1.5 hrs | ☐
▸ WEEK 6 (14 Apr – 20 Apr 2025)
14 Apr | Wk 6 | Ph 2 | 28 | Multi-Agent Systems | Orchestrator + worker pattern · agent communication · task decomposition · shared state | 2-agent system: planner + executor | 1 hr | ☐
15 Apr | Wk 6 | Ph 2 | 29 | Prompt Injection & Safety | What prompt injection is · indirect injection · detection strategies · output filtering · system prompt leakage | Audit your own app for 3 injection vectors | 1 hr | ☐
16 Apr | Wk 6 | Ph 2 | 30 | Multimodal — Vision API | Image + text prompts · base64 encoding · document understanding · screenshot analysis · use cases | App: analyse a screenshot and explain it | 1 hr | ☐
17 Apr | Wk 6 | Ph 2 | 31 | Advanced Output Parsing | Retry logic for malformed outputs · Pydantic V2 · instructor library deep dive · streaming + structured | Robust parser with auto-retry and validation | 1.5 hrs | ☐
18 Apr | Wk 6 | Ph 2 | 32 | Context Window Management | Sliding window · summarisation compression · selective retrieval · long-document strategies | Handle a 100-page doc without truncation | 1 hr | ☐
19 Apr | Wk 6 | Ph 2 | 33 | Week 6 Build Day — Multi-Agent System | Build a 3-agent pipeline: Researcher → Analyser → Writer · each agent has specific tools · planner orchestrates · output is a structured report | 3-agent pipeline producing reports | 4 hrs | ☐
20 Apr | Wk 6 | Ph 2 | — | Week 6 Review & Summary | Review multi-agent + safety + multimodal · write a safety checklist for LLM apps · plan Week 7 | LLM app safety checklist doc | 1.5 hrs | ☐
▸ WEEK 7 (21 Apr – 27 Apr 2025)
21 Apr | Wk 7 | Ph 2 | 34 | Batch Processing & Async | Async API calls · asyncio patterns · batch embedding · parallel retrieval · throughput vs latency | Async batch processor for embeddings | 1 hr | ☐
22 Apr | Wk 7 | Ph 2 | 35 | Prompt Versioning & Management | Prompt as code · version control strategies · A/B testing prompts · prompt registries | Simple prompt registry with version history | 1 hr | ☐
23 Apr | Wk 7 | Ph 2 | 36 | Agent Reliability Patterns | Timeout handling · partial failure recovery · checkpointing · human-in-the-loop interrupts | Add checkpoint + resume to your agent | 1.5 hrs | ☐
24 Apr | Wk 7 | Ph 2 | 37 | Phase 2 Agent Polish | Run full eval suite · fix top 3 failure modes · improve tool descriptions · tune system prompt | Agent passing 85%+ of eval suite | 1.5 hrs | ☐
25 Apr | Wk 7 | Ph 2 | 38 | Phase 2 Concepts Review | Review agents + evals + memory + retrieval + multi-agent + safety — fill any gaps | Personal Phase 2 gap analysis | 1 hr | ☐
26 Apr | Wk 7 | Ph 2 | 39 | Week 7 Build Day — Phase 2 Capstone | Combine everything: multi-tool agent + eval harness + memory + hybrid retrieval + safety checks · write comprehensive README with architecture diagram | Phase 2 capstone on GitHub | 4 hrs | ☐
27 Apr | Wk 7 | Ph 2 | — | Phase 2 Review & Retrospective | Write Phase 2 retrospective · what patterns you'd use again · what surprised you about agents in practice · plan Phase 3 | Phase 2 retrospective + Phase 3 plan | 1.5 hrs | ☐

## 🚀 Phase 3 — Production
Phase 3: Production Engineering ¦ 90-Day AI SME Plan
MON–FRI: 1–1.5 hrs learning ¦ SAT: 3–4 hrs build ¦ SUN: 1.5 hrs review & summary
Date | Week | Phase | Day | Topic | What To Study / Build | Deliverable | Time | ✅ Done
▸ WEEK 8 (28 Apr – 04 May 2025)
28 Apr | Wk 8 | Ph 3 | 36 | Latency Optimisation | Streaming · parallel tool calls · prompt caching (Anthropic) · model routing by complexity · first-token latency | Benchmark: measure p50/p95 latency for 3 strategies | 1 hr | ☐
29 Apr | Wk 8 | Ph 3 | 37 | Cost Optimisation | Token budgeting · model routing (small model first) · cache embeddings · batch API · cost calculator | Add per-query cost tracker to your app | 1 hr | ☐
30 Apr | Wk 8 | Ph 3 | 38 | Observability with LangSmith | Tracing setup · span attribution · tagging runs · prompt versioning in LangSmith · debugging failures | Full LangSmith tracing on your agent | 1 hr | ☐
01 May | Wk 8 | Ph 3 | 39 | Production Error Handling | Rate limits · exponential backoff · fallback models · circuit breaker pattern · dead letter queues | Production-grade retry + fallback system | 1.5 hrs | ☐
02 May | Wk 8 | Ph 3 | 40 | Logging & Debugging LLMs | Structured logging · request/response logging (safely) · debugging non-deterministic failures | Structured logging system for LLM calls | 1 hr | ☐
03 May | Wk 8 | Ph 3 | 41 | Week 8 Build Day — Production Hardening | Harden your Phase 2 agent: add streaming + cost tracking + LangSmith tracing + retry logic + structured logging · load test with 50 requests | Production-hardened instrumented agent | 3–4 hrs | ☐
04 May | Wk 8 | Ph 3 | — | Week 8 Review & Summary | Review latency + cost + observability · write your personal 'Production LLM Checklist' · plan Week 9 | Production LLM checklist doc | 1.5 hrs | ☐
▸ WEEK 9 (05 May – 11 May 2025)
05 May | Wk 9 | Ph 3 | 42 | Security — OWASP LLM Top 10 | Prompt injection · insecure output · data leakage · supply chain risks · model theft · mitigation strategies | Security audit of your own app against OWASP Top 10 | 1 hr | ☐
06 May | Wk 9 | Ph 3 | 43 | PII & Data Privacy | PII detection · redaction before sending to LLM · output scanning · GDPR considerations · presidio library | Add PII redaction pipeline to your app | 1 hr | ☐
07 May | Wk 9 | Ph 3 | 44 | Open-Source Models with Ollama | Ollama setup · run Llama 3 + Mistral locally · compare quality vs GPT-4o on 5 tasks · local vs cloud tradeoffs | Local model comparison report | 1 hr | ☐
08 May | Wk 9 | Ph 3 | 45 | Deployment with FastAPI + Docker | FastAPI wrapper for LLM app · Dockerfile · env config · API key management · health check endpoint | Dockerised FastAPI serving your LLM app | 1.5 hrs | ☐
09 May | Wk 9 | Ph 3 | 46 | Fine-Tuning Concepts | When to fine-tune vs prompt · LoRA · SFT · DPO · data requirements · cost vs quality tradeoff | Fine-tuning proposal for a hypothetical use case | 1 hr | ☐
10 May | Wk 9 | Ph 3 | 47 | Week 9 Build Day — Deploy Your App | Deploy your agent as a REST API · add JWT auth · rate limiting · CORS · health checks · basic monitoring endpoint · test with Postman | Live REST API (local or cloud) | 3–4 hrs | ☐
11 May | Wk 9 | Ph 3 | — | Week 9 Review & Summary | Review security + privacy + deployment · write deployment runbook · plan Week 10 | Deployment runbook doc | 1.5 hrs | ☐
▸ WEEK 10 (12 May – 18 May 2025)
12 May | Wk 10 | Ph 3 | 48 | Monitoring in Production | Custom quality metrics · alerting on regression · user feedback loops (thumbs up/down) · dashboards | Add feedback collection + quality metrics to API | 1 hr | ☐
13 May | Wk 10 | Ph 3 | 49 | Testing LLM Applications | Unit testing prompts · integration tests · snapshot tests · red-teaming your own app | Test suite with 20+ automated tests | 1.5 hrs | ☐
14 May | Wk 10 | Ph 3 | 50 | Architecture Decision Framework | RAG vs fine-tune vs agent vs simple prompt · decision flowchart · real case studies analysis | Architecture decision flowchart you'll reuse | 1 hr | ☐
15 May | Wk 10 | Ph 3 | 51 | Phase 3 Project Polish | Full production hardening: security + monitoring + tests + docs + architecture diagram | Production-grade app with complete docs | 1.5 hrs | ☐
16 May | Wk 10 | Ph 3 | 52 | Record Demo + Update Portfolio | Record a 5-min walkthrough video · update GitHub · write project description for LinkedIn | Demo video + LinkedIn update | 1 hr | ☐
17 May | Wk 10 | Ph 3 | 53 | Week 10 Build Day — Phase 3 Capstone | Build a fully production-ready API: auth + rate limiting + monitoring + security + tests + Docker + CI pipeline · comprehensive README | Phase 3 capstone: production-grade API | 4 hrs | ☐
18 May | Wk 10 | Ph 3 | — | Phase 3 Review & Retrospective | Write Phase 3 retrospective · compare your app now vs Phase 1 · list 5 things you'd do differently · plan Phase 4 | Phase 3 retrospective + Phase 4 plan | 1.5 hrs | ☐

## 🏆 Phase 4 — Specialise
Phase 4: Specialisation & Portfolio ¦ 90-Day AI SME Plan
MON–FRI: 1–1.5 hrs learning ¦ SAT: 3–4 hrs build ¦ SUN: 1.5 hrs review & summary
Date | Week | Phase | Day | Topic | What To Study / Build | Deliverable | Time | ✅ Done
▸ WEEK 11 (19 May – 25 May 2025)
19 May | Wk 11 | Ph 4 | 51 | Choose Vertical + Plan Capstone | Evaluate 4 verticals: autonomous agents / multimodal / fine-tuning / AI infra · choose one · write detailed 2-week build plan | Written capstone project plan | 1 hr | ☐
20 May | Wk 11 | Ph 4 | 52 | Vertical Deep Dive — Day 1 | Read primary papers/docs for your vertical · implement the simplest possible version of the core concept | Proof-of-concept for capstone core feature | 1.5 hrs | ☐
21 May | Wk 11 | Ph 4 | 53 | Vertical Deep Dive — Day 2 | Build on Day 1 · solve the hardest technical problem in your vertical · ask: what would break in production? | Core feature working + edge cases handled | 1 hr | ☐
22 May | Wk 11 | Ph 4 | 54 | Competitive Landscape Research | Survey tools, startups, OSS projects in your vertical · identify gaps · think about where you add value | Landscape map / competitive analysis doc | 1 hr | ☐
23 May | Wk 11 | Ph 4 | 55 | System Design for AI Apps | Design a scalable AI system: data flow · model selection · APIs · storage · cost model · failure modes | Architecture diagram for a realistic AI product | 1 hr | ☐
24 May | Wk 11 | Ph 4 | 56 | Week 11 Build Day — Capstone v0.1 | Build the core of your capstone project · focus on the unique value proposition · push to GitHub with initial README | Capstone v0.1 on GitHub | 4 hrs | ☐
25 May | Wk 11 | Ph 4 | — | Week 11 Review & Summary | Review vertical research + system design · write a 'Why I chose this vertical' post draft · plan Week 12 | Draft blog post + Week 12 plan | 1.5 hrs | ☐
▸ WEEK 12 (26 May – 01 Jun 2025)
26 May | Wk 12 | Ph 4 | 57 | Interview Prep — Core AI Concepts | Common AI eng interview topics: RAG internals · agent loops · eval design · latency trade-offs · fine-tuning when/why | Personal cheat sheet: 30 key concepts + your answers | 1 hr | ☐
27 May | Wk 12 | Ph 4 | 58 | Interview Prep — System Design | Practice designing: semantic search engine · code review bot · customer support agent · medical Q&A system | Write-up for 2 full system design problems | 1.5 hrs | ☐
28 May | Wk 12 | Ph 4 | 59 | Capstone — Feature Complete | Finish all core features · add error handling · write clear architecture section in README | Feature-complete capstone | 1 hr | ☐
29 May | Wk 12 | Ph 4 | 60 | Technical Blog Post — Draft | Write 1000-word post: something you built, a lesson learned, or a deep-dive on a pattern you mastered | Blog post draft ready for review | 1.5 hrs | ☐
30 May | Wk 12 | Ph 4 | 61 | Blog Post — Publish | Edit + publish on Medium or Dev.to · share on LinkedIn · add to portfolio | Published blog post with live link | 1 hr | ☐
31 May | Wk 12 | Ph 4 | 62 | Week 12 Build Day — Capstone Polish | Polish capstone: add tests + monitoring + deployment + demo GIFs in README · make it something you're proud to show | Portfolio-ready capstone project | 4 hrs | ☐
01 Jun | Wk 12 | Ph 4 | — | Week 12 Review & Summary | Review interview prep + capstone status · practice explaining your capstone out loud for 5 min · plan Week 13 | 5-min verbal pitch + Week 13 plan | 1.5 hrs | ☐
▸ WEEK 13 (02 Jun – 08 Jun 2025)
02 Jun | Wk 13 | Ph 4 | 63 | Portfolio Polish — GitHub | 3 pinned repos · clean READMEs with GIFs · consistent naming · architecture diagrams · tech stack badges | Polished GitHub profile ready to share | 1 hr | ☐
03 Jun | Wk 13 | Ph 4 | 64 | AI Community Engagement | Join AI Discord/Slack communities · comment on 3 GitHub issues · tweet a finding · connect with 5 AI engineers on LinkedIn | First public community contributions | 1 hr | ☐
04 Jun | Wk 13 | Ph 4 | 65 | Demo Video Preparation | Script a 10-min demo of your capstone · practice explaining every design decision · record and review | Demo video script + first recording | 1.5 hrs | ☐
05 Jun | Wk 13 | Ph 4 | 66 | Final Interview Prep | Mock technical interview: explain RAG, agents, evals out loud · practice system design whiteboarding · review your own code | Mock interview self-assessment doc | 1 hr | ☐
06 Jun | Wk 13 | Ph 4 | 67 | 90-Day Final Review | Read through all retrospectives · identify your top 5 skills gained · list remaining gaps for continued learning · celebrate 🎉 | 90-day retrospective document | 1 hr | ☐
07 Jun | Wk 13 | Ph 4 | 68 | 🎓 Graduation Build Day | Final polish: update all READMEs · record final demo video · update LinkedIn with AI Engineer skills · draft job applications · write 'What I learned in 90 days' post | Complete portfolio + LinkedIn update + job apps | 4 hrs | ☐
08 Jun | Wk 13 | Ph 4 | — | 🎉 Retrospective & Next Steps | Write your final retrospective · define next 90-day learning plan · celebrate what you've built · rest well — you've earned it | Next 90-day plan + final retrospective | 1.5 hrs | ☐

## 📚 Resources
📚 Curated Resources — AI Application Development SME
Resource | Link | Description | Best For
── DOCUMENTATION ──
Anthropic Docs | docs.anthropic.com | Prompt engineering, tool use, vision, caching | Ph 1–2
OpenAI Platform | platform.openai.com/docs | Function calling, fine-tuning, assistants API | Ph 1–2
LangChain Docs | python.langchain.com | LCEL, chains, agents, LangGraph | Ph 2
LlamaIndex Docs | docs.llamaindex.ai | RAG pipelines, query engines, routers | Ph 2
LangSmith Docs | docs.smith.langchain.com | Tracing, evals, prompt versioning | Ph 3
── PAPERS TO READ ──
Attention Is All You Need | arxiv.org/abs/1706.03762 | Original transformer paper — builds intuition | Ph 1
REALM (RAG Paper) | arxiv.org/abs/2005.11401 | Foundational RAG architecture | Ph 2
ReAct Agent Paper | arxiv.org/abs/2210.03629 | Reason + Act agent pattern | Ph 2
Constitutional AI (Anthropic) | arxiv.org/abs/2212.08073 | Safety and alignment in practice | Ph 3
── COURSES & VIDEOS ──
DeepLearning.AI Short Courses | deeplearning.ai/short-courses | RAG, agents, evals, LangChain — free & fast | Ph 1–2
Andrej Karpathy — Intro to LLMs | youtube.com/@karpathy | Best conceptual LLM intuition builder | Ph 1
Hamel Husain — LLM Evals | hamel.dev | Definitive practitioner guide to evals | Ph 2
AI Engineer Summit Talks | youtube.com — AI Engineer Summit | Conference talks by practitioners | Ph 3–4
── TOOLS & LIBRARIES ──
Instructor | jxnl.github.io/instructor | Structured outputs with Pydantic + retry | Ph 2
Chroma DB | trychroma.com | Local vector DB, great for prototyping | Ph 1–2
Ollama | ollama.ai | Run open-source LLMs locally | Ph 3–4
Presidio | microsoft.github.io/presidio | PII detection and redaction | Ph 3
── COMMUNITIES ──
Latent Space Podcast | latent.space | Best AI engineering podcast, weekly | Ongoing
r/LocalLLaMA | reddit.com/r/LocalLLaMA | Open-source model news and discussion | Ongoing
Hugging Face Discord | discord.gg/huggingface | Active community for model questions | Ongoing